## Log
Date | Name | Start Time | End Time | Total Time | Issue | Notes
2020-02-05 | Jenna | 13:00 | 17:30 | 1:00 | Camera | Worked on creating a camera that followed the player as the player moves (while at work)
2020-02-06 | Wallace | 13:00 | 15:15 | 2:15 | Movement | Worked to improve movement system to allow movement in multiple directions simultatiously
2020-02-06 | Jenna | 13:00 | 14:00 | 1:00 | Shadows | Created presentation, worked with Wallace, added shadows
2020-02-07 | Allen | 8:00 | 9:00 | 1:00 | Empty Room | Base template of a room for the levels
2020-02-08 | Wallace | 15:00 | 17:45 | 2:45 | Movement/Loading | Added a loading screen and kept main renderer from running until everything was loaded
2020-02-08 | Jenna | 15:30 | 17:30 | 2:00 | Hopping | Played with collision eventhandling and added a broken hopping movement
2020-02-10 | Jenna | 9:00 | 9:30 | 0:30 | Fixing shadows | Ran into problems
2020-02-10 | Jenna | 19:30 | 22:00 | 2:30 | Shadows
2020-02-10 | Allen | 8:00 | 9:00 | 1:00 | Empty Room | Worked on Empty Room template
2020-02-10 | Allen | 19:15 | 20:30 | 1:15 | Empty Room | Finished Empty Room with planes, made a test floor with box object in Room_Template
2020-02-11 | Allen | 14:00 | 15:00 | 1:00 | Empty Room Research | Trying to figure out best route for optimization reasons
2020-02-11 | Wallace | 11:45 | 15:15 | 3:30 | Movement | Trying to fix reseting posistion causing stuttering
2020-02-11 | Jenna | 12:00 | 14:00 | 2:00 | Shadows | Finally found a solution
2020-02-12 | Wallace | 11:00 | 12:30 | 1:30 | Movement/object interaction | Fixed movement, no more stuttering on reset. Added obsisticals to navagate around
2020-02-13 | Wallace | 13:30 | 15:15 | 1:45 | Character Switching/ Movement
2020-02-13 | Jenna | 20:00 | 21:30 | 1:30 | Rewrapped plane | Enabled shadows successfully, added ambientlight
2020-02-13 | Allen | 18:30 | 20:30 | 2:00 | Room Test | Made a quick Room Template in blender, hacked code together from other demos into Allens_Test
2020-02-14 | Allen | 13:00 | 14:30 | 1:30 | Room Test | Reworked Allens_test into a pretty decent looking room
2020-02-15 | Jenna | 12:30 | 15:30 | 3:00 | Central Impulse, dirty positions | Worked on a fix for studdering/choppy graphics. Settled on modifying WebGL
2020-02-17 | Wallace | 11:00 | 15:25 | 4:25 | Level/ Movement | nix jumping for now
2020-02-18 | Jenna | 12:00 | 14:00 | 2:00 | Modified Shadows | Shadow Softmap enabled
2020-02-15 | Allen | 18:00 | 20:00 | 2:00 | Allens_Test | Incorporated other code into Allens_Test to use light and shadows
2020-02-20 | Wallace | 12:30 | 15:15 | 2:45 | Jumping | Fixed jumping by using raycaster
2020-02-23 | Jenna | 19:00 | 23:00 | 4:00 | Collision detection | Trigger event when objects collide/intersect. (Collision detection, may have to use raycaster later)
2020-02-23 | Wallace | 14:00 | 17:00 | 3:00 | Level Selection | Added Levels class to make level selection easier
2020-02-24 | Wallace | 12:00 | 15:30 | 3:30 | Memory Leak | There was a memory leak caused by our Levels class
2020-02-24 | Wallace | 16:30 | 17:00 | 0:30 | Model Loading | Fixing the memory leak lead to an issue with model loading, however it has been fixed
2020-02-24 | Allen | 9:30 | 11:00 | 1:30 | Modularization | Started to modularize controls, camera, etc...not working yet
2020-02-25 | Allen | 8:00 | 9:00 | 1:00 | Levels | Redrew levels in ms paint so theyre easier to see
2020-02-25 | Jenna | 12:00 | 14:00 | 2:00 | Demo, presentation | Got presentation together and continued to do testing/research
2020-02-27 | Wallace | 12:00 | 15:30 | 3:30 | Level Loading/Fixing Jumping Bug | When leaving a level the jumpCaster.far remained the size of the last selected prop meaning that if jumpcaster.far was set to a smaller objects value, when returning to the level the player could not detect the ground beneth them and therefore could not jump
2020-03-01 | Jenna | 17:00 | 21:00 | 4:00 | New Level | Setup room for another level, added a few objects, changed their properties
2020-03-02 | Jenna | 9:30 | 11:00 | 1:30 | Hollow Cylinder
2020-03-02 | Wallace | 11:30 | 14:00 | 2:30 | Menu Edits/Level Building | Slightly modified menu, starting building level one (Living Room)
2020-03-02 | Allen | 14:00 | 16:15 | 2:15 | Models/Level1 | Found a set of Living Room Objects and a pretty chill mouse, converted em to glb and am makin a living room
2020-03-03 | Allen | 13:00 | 15:00 | 2:00 | Tutorial | tryin to get the living room set to work with physics 'n stuff
2020-03-03 | Wallace | 11:30 | 15:20 | 3:50 | Menus/Jumps
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## Total Hours
Total Hours
Wallace | 35:45
Jenna | 27:00
Allen | 15:30